## Multi Year Accessibility Plan
a division of Lift Temp Inc.
2014 to 2019 Multi-Year Accessibility Plan
Integrated Accessibility Standards Regulation (IASR)
The table below is the 2013-2018 Accessibility Plan for the Integrated Accessibility Standards Regulation. The table has 4 columns and 48 rows. To navigate through the table use your down arrow key. Once in the table use your tab key. You will be notified that you are at the end of the table.
General Deliverables | Completed | Legislated Date (January)
Policies & Procedures |  | 2014
Create Policies with Statement of Organizational Commitment in written form | Completed | 2014
Approval and Sign off | Completed | 2014
Make available to the Public | Completed | 2014
Available in Alternative Formats - upon request | Upon Request | 2014
Accessibility Plan - Multi Year |  | 2014
Develop Accessibility Plan | Completed | 2014
Accessibility Plans - Post to web | Completed | 2014
Continue to work on Accessibility Plan, review progress and update. Update regularly and every five years. | Ongoing | 2014-2018
Provide in alternative format | Upon Request | 2014
Accessibility Self Service Kiosk - have regard for accessibility when purchasing | N/A | 2014
Training - All employees & volunteers, policy developers, those providing goods or services on behalf of organization regarding IARS and Human Rights Code | Completed, Ongoing | 2015
Decide on training delivery | Completed
Create training schedule for current staff and new staff | Completed, Ongoing
Ensure sign in sheets for record keeping | Completed, Ongoing
Training completed | Completed | 2015
Continue to train new staff as part of orientation | Completed, Ongoing | 2015-2018
Information & Communications | Completed | Legislated Date (January)
Emergency Procedure Plans or Public Safety Information - inventory and make accessible | Completed | 2012
Feedback - ensure feedback system accessible | Completed | 2015
Accessible formats and communication supports upon request (timely manner, no cost charged if none charged to other persons) | Upon Request | 2016
Create inventory of current documents | Completed
Create document renewal plan | Ongoing
Create Strategic Communication Plan -create processes for flow of documents, who creates source documents, who ensures pdf's are accessible, who checks for accessibility before posting to website, decide on corporate wide fonts, staff training on accessible document creation, analysis of website content and new content | Ongoing
If creating a new Website WCAG 2.0 Level AA (other then closed caption Live pre-recorded audio) |  | 2014
All internet websites and web content WCAG 2.0 Level AA | Working towards | 2021
Review all content on website back to 2012 to ensure everything is accessible | Working Towards | 2021
Employment | Completed | Legislated Date (January)
HR Staff develop deliverables and processes | Completed
Workplace Emergency Response for staff | Completed | 2012
Recruitment - notify employees and public regarding availability of accommodation | Completed | 2016
Notify applicant - availability of accommodation upon request for assessments or selection process | Completed | 2016
Inform employees of policies regarding job accommodations | Completed | 2016
Providing accessible formats and communication supports available to perform job | Completed | 2016
Have a Documented Individual Accommodation Plan (IAP) | Completed | 2016
Have a Return to Work Process | Completed | 2016
Performance Management takes into account accessibility needs | Completed | 2016
Career Development and Advancement Process takes into account accessibility needs | Completed | 2016
Redeployment process takes into account accessibility needs | Completed | 2016
Continue to proactively remove barriers across employment life cycle allowing employees to reach their full potential | Ongoing | 2016-2018
Public Spaces | Completed | Legislated Date (January)
Incorporate Design of Public Spaces on newly developed or redeveloped recreational trails and beach access routes, outdoor public use eating areas, outdoor play spaces, exterior paths of travel, accessible parking and service related elements | N/A | 2017
If developing recreational trails consult with public and persons with disabilities | N/A | 2017
Provide maintenance and restoration | N/A | 2017
Develop procedures for preventative and emergency maintenance of accessible elements in public spaces | N/A | 2017
Develop procedures for dealing with temporary disruptions when accessible elements under public spaces not working | N/A | 2017
Report on Public Spaces every three years | N/A | 2020 end of chart
End of table